## JiraBacklog
Summary | Work Type | Description | Priority | Story Point Estimate | Component
US-01 - Scan medicine into inventory | Story | As a pharmacy technician, I want to scan a medicine and enter quantity, batch, and expiry so inventory records stay accurate. | High | 5 | Inventory
US-02 - Show low-stock and expiry alerts | Story | As a pharmacist, I want low-stock and near-expiry items flagged automatically so I can act early. | High | 3 | Inventory
US-03 - Add product to sale by barcode or search | Story | As a staff pharmacist, I want to add a product by barcode scan or search so I can build a sale quickly. | Highest | 3 | POS
US-04A - Record sale and deduct stock | Story | As a staff pharmacist, I want completing a sale to record the transaction and deduct stock so inventory stays synchronized. | Highest | 5 | POS
US-04B - Print receipt after sale | Story | As a staff pharmacist, I want a receipt printed after a completed sale so the customer has a transaction record. | Medium | 2 | POS
US-05 - Search customer history | Story | As a pharmacist, I want to search for a customer and view prescription and purchase history so I can review prior records quickly. | Medium | 3 | Customer Records
US-06 - Link sale or prescription to customer | Story | As a pharmacist, I want to associate a sale or prescription with a customer so the history remains searchable. | Medium | 3 | Customer Records
US-07 - Rank shortage-risk items | Story | As an owner-pharmacist, I want shortage-risk items ranked by urgency so I know what needs attention first. | High | 5 | Smart Stock
US-08 - Explain Smart Stock recommendation | Story | As an owner-pharmacist, I want to see demand, stock, supplier lead time, and days of cover so I understand a recommendation. | High | 3 | Smart Stock
US-09 - Keep stock suggestions advisory | Story | As an owner-pharmacist, I want stock suggestions to require confirmation so I retain control over purchasing. | Highest | 2 | Smart Stock
US-10 - Show actionable dashboard | Story | As a pharmacy owner, I want the homepage to show low stock, expiry risk, recent sales, and stock totals so I can see the pharmacy state quickly. | High | 5 | Dashboard
US-11 - Open filtered inventory from alert | Story | As a staff member, I want an alert to open the relevant filtered inventory view so I do not have to search manually. | High | 3 | Dashboard
US-12 - Edit suggested reorder quantity | Story | As an owner-pharmacist, I want to edit a suggested reorder quantity before adding it to a draft so the order reflects my judgment. | High | 3 | Smart Stock
US-13 - Review reorder draft before confirmation | Story | As an owner-pharmacist, I want to review the full draft before confirmation so no recommendation becomes an order without approval. | High | 5 | Smart Stock
US-14A - Scan and enter delivery line | Story | As a pharmacy technician, I want to scan an incoming medicine and enter quantity, batch, and expiry in one screen so delivery entry is fast. | High | 5 | Inventory
US-14B - Confirm delivery and update inventory | Story | As a pharmacy technician, I want delivery lines saved as a draft until I confirm them so inventory is not changed prematurely. | High | 3 | Inventory
US-15 - Warn about duplicate batch or close expiry | Story | As a pharmacy technician, I want warnings for duplicate batches or unusually close expiry dates so I can correct questionable delivery data. | High | 3 | Inventory
DEV-01 - Create local database schema | Task | Define tables and relations for products, batches, sales, customers, prescriptions, suppliers, reorder drafts, and audit entries. | High |  | Platform
DEV-02 - Implement login and basic roles | Task | Add authenticated staff accounts with simple permissions for sensitive actions. | High |  | Platform
DEV-03 - Implement backup and restore | Task | Support local backup and restore without losing transaction history. | High |  | Platform
DEV-04 - Add audit logging | Task | Record important inventory, sale, and reorder changes with user and timestamp. | Medium |  | Platform
DEV-05 - Integrate barcode scanner input | Task | Accept common keyboard-style barcode scanner input in POS and receiving workflows. | High |  | Hardware
DEV-06 - Integrate receipt printer | Task | Print a simple receipt after a completed sale. | Medium |  | Hardware
DEV-07 - Test critical inventory and POS workflows | Task | Add automated and manual tests for stock deduction, delivery confirmation, and rollback on failure. | High |  | Quality